## Sheet1
FY | Location | Scope of Work | Contractor | Budget Estimate | Schedule | Comments
17-18 | Carver | LED Lights |  | 150000 | Spring/Summer | Out for Proposal
17-18 | Fair | Track Overlay | Redstone | 400000 | Fall '17 | In Progress
17-18 | Scott Field | Stadium Improvements |  | 2000000 | Spring/Summer | In Design
17-18 | McClellan | New Press Box |  | $60,000 + | Winter/Spring | Out for Bid
17-18 | " | Field Improvements |  | 200000 | Winter/Spring | Schedule to bid Jan '18
17-18 | Fair | New Press Box |  | $60,000 + | Winter/Spring | Out for Bid
17-18 | " | Field Improvements |  | 25000 | Winter/Spring | Schedule to bid Jan '18
17-18 | Rockefeller | EC Playground |  | 150000 | Winter/Spring
17-18 | Metropolitan | Cooling Tower | Middleton | 40000 | Winter
17-18 | Dunbar | Elevator |  | 100000 | Open
17-18 | Facilities Services | Roof |  | 250000 | Open | Design Complete
|  | Total= |  | 3315000
18-19 | Washington | Rest Rooms |  | 250000 | Summer
18-19 | Watson | Roof |  | 1100000 | Open
18-19 | Terry | Roof |  | 1000000 | Open
18-19 | Henderson | Roof |  | 1100000 | Open
18-19 | Rockefeller | Fire Alarm Upgrade |  | 150000 | Summer
18-19 | Henderson | RTU's |  |  | Summer
18-19 | King | Boiler |  | 30000 | Summer
18-19 | King | LED Lights |  | 150000 | Summer
18-19 | Dunbar | Fresh Air Units |  |  | Summer
18-19 | Dunbar | Kitchen & GYM A/C |  | 300000 | Summer
18-19 | Dunbar | Waterproofing |  | 100000 | Open
18-19 | Parkview | GYM A/C |  | 380000 | Spring/Summer
18-19 | Mann | GYM/ Kitchen A/C |  | 380000 | Spring/Summer
18-19 | Brady | Kitchen A/C |  | 275000 | Summer
18-19 | McDermott | Kitchen A/C |  | 70000 | Summer
18-19 | Terry | Kitchen A/C |  | 80000 | Summer
18-19 | Terry | New Boiler |  | 30000 | Summer
18-19 | Baseline | Kitchen A/C |  | 125000 | Summer
18-19 | Wakefield | Kitchen A/C |  | 25000 | Summer
18-19 | Watson | Kitchen A/C |  | 100000 | Summer
18-19 | Hall | Swale 600 & 700 Wing |  | 20000 | Summer
18-19 | PVMS | Stadium Lights |  | 200000 | Spring/Summer
18-19 | Admin | Parking Lot |  | 33000 | Summer
18-19 | Facilites Services | Parking Lot |  | 85000 | Open
18-19 | Hall | GYM A/C |  | 400000 | Winter/Spring | In Design
18-19 | " | Kitchen A/C |  | 115000 | Summer
18-19 | Fair | Gym A/C X's 2 |  | 500000 | Summer
18-19 | McClellan | Gym A/C X's 2 |  | 500000 | Summer
|  | Total= |  | 7498000
19-20 | PH Elem & Mid | Roof |  | 1500000 | Open
19-20 | McDermott | Roof |  | 1000000 | Open
19-20 | Baseline | Roof |  | 1750000 | Open
19-20 | Mabelvale Elem | Kitchen A/C |  | 50000 | Summer
19-20 | " | Fresh Air Replacement |  |  | Summer
19-20 | Chicot | Kitchen A/C |  | 50000 | Summer
19-20 | Booker | Kitchen A/C |  | 200000 | Summer
19-20 | Gibbs | Kitchen A/C |  | 140000 | Summer
19-20 | Pulaski Heights | Kitchen A/C |  | 75000 | Summer
19-20 | " | Gym A/C |  |  | Summer
19-20 | Fair Park | Kitchen A/C |  | 50000 | Summer
19-20 | Forest Heights | Gym/Kitchen A/C |  | 350000 | Summer
|  | Total= |  | 5165000
20-21 | Dodd | Kitchen A/C |  | 52500 | Summer
20-21 | Western Hills | Kitchen A/C |  | 65000 | Summer
20-21 | " | Fresh Air Replacement |  |  | Summer
20-21 | Williams | Kitchen A/C |  | 70000 | Summer
20-21 | " | Fresh Air Replacement |  |  | Summer
20-21 | Jefferson | Fresh Air Replacement |  |  | Summer
20-21 | Romine | Fresh Air Replacement |  |  | Summer
20-21 | Bale | Fresh Air Replacement |  |  | Summer
20-21 | Jefferson | Roof |  | 900000 | Open
20-21 | Metro "A" Bldg | Roof |  | 1100000 | Open
20-21 | CN Warehouse | Roof |  | 275000 | Open
20-21 | Pulaski Heights | Fresh Air & HVAC Replacement |  |  | Summer
20-21 | Dunbar | HVAC Replacement |  |  | Summer
|  | Total= |  | 2462500
| SWLRHS | New Construction |  | 55000000 |  | Currently clearing site for construction
|  | Grand Total= |  | 73440500